Criteria for measuring CEOP Progress

| Integrated Data Sets | Reference Site Composite Data Archive by UCAR | F | EOP-1: completed EOP-3 1st half: almost completed EPO-3 2nd half: on-going |
| --- | --- | --- | --- |
|  | Model Output Archive by MPI, 9 NWP centers and 2 Data Assimilation Centers | F | 5 Centers’ Outputs: on-going |
|  | Satellite Products Output by UT and JAXA | F | TMI,PR, SSM/I, AMSR, AMSR-E, AIRS, AVHRR, GMS: on-going |
|  | Data Integration Service: Distributed Integration System by JAXA and CEOS/WGISS Centralized Integration System by UT | I-F | Demonstration at the 10th GHP |
| WESP | Water and Energy Budget | Pr | 3 articles on the CEOP Newsletter Report to the 10th GHP GLDAS Product generation: on-going |
|  | NWP Model Output Validation (NCEP, JMA, GMAO, ECPC) | Pr |  |
|  | GLDAS | Pr |  |
|  | GHP/CEOP Model Transferability Study | B |  |
|  | Model Inter-comparison Study | B |  |
| CIMS | Monsoon Intercomparison Study | Pr | 1 article on the CEOP Newsletter 2 Workshops (Milan, Montevideo) |
|  | Diurnal, Intraseasonal and Seasonal Variability | Pr |  |
|  | Monsoon Process Study by Using Global and/or Regional Models | B |  |
|  | Impacts of Local & Remote Forcings on Monsoon | B |  |
| Satellite | Algorithm Development and Validation (Soil Moisture, Snow) | Pr | 2 articles on the CEOP Newsletter |
|  | Satellite Data Assimilation for Land Hydrology(Soil Moisture, Snow) | Pr | 2 journal papers |
| Project Management | Regular Conference Call | F | overall, model, data integration, regional |
|  | Newsletter | F | Twice a year (No.1 to No.6) |
|  | CEOP Plenary Meeting | F | Once a year (Tokyo, Berlin, Irvine) |
|  | Workshop | F | 4 (Berlin, Milan, Irvine, Montevideo) |

Technical Requirements, P, I, F (Planned, Initiating, Functioning)

Scientific Requirements B, Pr, C (Beginning, Progressing, Completed)

CEOP Phase Approach:

CEOP I: Data Collection

Establishment of

- Data and Products Collection Framework: Coordination among Reference Sites, NWP Centers and Space Agencies

- Data Processing Framework: 		International Cooperation for Data Archiving and Data Integration Services

- Scientific Framework			Focusing on Commonality and Particularity of the Climate System and Quantitative Analysis

CEOP II: Research and System Expansion toward Global Energy and Water Cycle Observation System of Systems (preliminary idea)

Part-I(2005-2006)

- CEOP-I Science Goal (WESP and CIMS) Accomplishment by Using CEOP-I Data Sets

- Building a GEOSS Water Cycle Observation and Data System based on CEOP-I under the framework of GEOSS 10-Year Implementation Plan

Part-II(2007-2010)

- Implementation of the CEOP-II Integrated Observation and Data System for the Global Energy and Water Cycle

- CIMS: Contribution to WCRP Pan Monsoon Study and

- WESP: Extension to Down-scaling Studies, its application to IWRM, and model transferability Studies

- Cold Region Study in Cooperation with CliC

- Extreme Event Mechanism

- Aerosols-Water Cycle Interaction.

CEOP-II Planning Schedule (proposal)

Comments, suggestions and additional key elements: by Oct. 20

First draft for each key element: by Nov. 20

Assembling: by Nov. 30

First review: by Dec. 20

Discussion, suggestion at GEWEX SSG: Jan.31 to Feb. 4

Scientific and implementation discussion for finalizing the plan at CEOP-IGWCO joint meeting in Tokyo